| Division of Finance and Business Operations |  | Procurement & Strategic Sourcing 5700 Cass Avenue, suite 4200 Detroit, Michigan 48202 (313) 577-3734 FAX (313) 577-3747 |
| --- | --- | --- |

3/11/15

Addendum #1 To

Request for Proposal

For Scott Hall Roof Replacement: Project 612-256214

Minutes of the Pre-bid Conference

Dated March 4, 2015

The Addendum must be acknowledged on your lump sum bid.

The pre-bid conference for Request for Proposal for Scott Hall Roof Replacement, Project 612-256214 was held on March 10, 2015, at 3:00 p. m. (local time) – at Detroit, MI 48202.  Robert Kuhn, Sr. Buyer, reviewed the highlights of the pre-bid package, especially concerning details such as bid due dates and who Contractors may contact during the live bid process.  Robert Jacobs from WSU Design and Construction Services and Ellen Rotter  from NSA Architects, Engineers, Planners   discussed the site layout and staging, fencing and signage and coordination expectations with WSU and Contractors, technical aspects of the project and bid requirements, and conducted the Q & A session.

NOTE: You must have attended a pre-bid conference in order to be eligible to bid on a particular project.  Receipt of minutes or addenda without being at a pre-bid conference does not qualify your company to bid.

Numerous simple questions and answers were addressed at the pre-bid meeting. Some of the issues were as follows:

- A second walk thru has been scheduled for Monday, March 16, 2015, at 1:00  p. m.  Meet at the reception desk in Scott Hall.  No special accommodations for late arrivals.  Question from second walk-thru must be submitted in writing before due date for questions on 3/17/2015 at 12:00 PM (Noon).   The walk thru will begin promptly at 1:00  p. m.

- A bid bond is not required for bids below $50,000.  Otherwise, a bid bond (5%) will be required for the full amount of the bid.

- Performance Bond and Material & Labor Payment Bond requirements are listed in the specifications of the job.  Performance & Material & Labor Payment Bonds must be provided by the awarded Contractor with the submission of the signed contract; which will then be submitted to FP&M management for counter signature.

- The awarded Contractor must provide the required Certificate of Insurance in compliance with Section 800, article 11 of the bid specifications prior to commencement of any work.  Insurance requirements have recently been changed, contractors must review insurance requirements.  Note, Professional Liability Coverage is not required on this project, see section 800 – 8, Article 11 – Insurance (revised 2-06-2015), Point 4.

- Please review the insurance section carefully, there are some changes in the documents,  such as changes in the amounts of required insurance for most of the categories

- If your company has not previously done business with the University you may go to the Purchasing website at www.purchasing.wayne.edu and look for the “new vendor” link under “Information for Vendors” on the left.  You may submit a new vendor request form and an IRS form W-9.  This will register your company on our vendor list.  (NOTE: this does not replace the List-Serv.)

- This Project Requires the Contractor and any subcontractors to compensate all employees who come to the job site at no less than State of Michigan Prevailing Wage Rates.  A Prevailing Wage Rate Schedule is included in Section 00410 of the Bid Specifications.  Contractors must review these requirements to be sure they are in compliance with the requirements of the University and the State of Michigan. Contact the State of Michigan if further information on prevailing wage rate is needed at website http://www.michigan.gov/dleg/0,1607,7-154-27673_27706---,00.html.  Contractors must post wages at the job site in compliance with the complete Prevailing Wage Rate listing provided in Bid Documents.

- 1099 workers and subcontractors using 1099 workers are NOT acceptable

- Certified Payroll must be provided with each of the contractor’s pay applications for all workers who worked at the job site, in compliance with the State of Michigan policy.  Failure to provide certified payroll will constitute breach of contract and pay applications will be returned unpaid.  They will remain so until satisfactory supporting documents are provided.

- Signed waivers from all Subcontractors and suppliers must accompany Pay Applications or they will be returned for such documentation prior to approval.

- A properly executed sworn statement is required from all tiers of contractors, and sub-contractors indicating sub-contractors and suppliers which provide services or product of $1,000.00 or greater.  Sworn statements must accompany applications for payment

- All documents listed in the Front End Section 0410-2 “Wayne State Prevailing Wage Requirements” must accompany applications for payment. Failure to do so will result in the entire application package returned for correction.

- A checklist of all Pay Application requirements can be found in Section 00430-1.  A payment application meeting will be held at the start of the project for identification of required items.

- The competency and responsibility of Bidders will be considered in making the award.  The Owner does not obligate himself to accept the lowest or any other bids.  The Owner reserves the right to reject any and all bids and to waive any informalities in the Proposals

- Parking on WSU campus lots and structures are $7.00/access.  Contractor must build parking into their lump sum bid.  There is no parking allowed on the malls.

- Section 300, Form of Proposal has changed very recently, review carefully and complete in its entirety to avoid disqualification.

- The contractors must fill out our prequalification form.  They can attach additional information if they would like but at a minimum the information requested must be filled in on our form so that we do not have to hunt to find the information.

- Contractors who have withdrawn a bid after a University bid opening and/or refused to enter into a contract with the University upon notification of award within the last 3 years are not eligible to bid on this project.

- Project hours of operation are 7:00am – 7:00 pm, Monday thru Saturday. No activities between 7PM and 6AM.  Anything else requires advance notice and approval.

- Prequalification meeting will be held the first business day after bid openings.  Contractors must be available.  The Project Manager will coordinate the meetings.

- Prequalification meeting includes Schedule of Values from the Contractor, including a list of Contractor’s subcontractors and other qualifications required by the documents.

- An unsigned contract will be given to the successful Contractor at the conclusion of the Prequalification meeting, if all aspects of the bid are in order.  The Contractor has 5 business days to return the contract to the Project Manager for University counter signature.  The contractor must also submit a Performance Bond as outlined above and a Certificate of Insurance in the same 5 business day period.  In the event the Contractor fails to return the documents in this 5 day period, the University reserves the right to award the contract to the next most responsive bidder.

- The contractor must maintain all weathertight roofing provisions during the removal and replacement of the roof and associated items.   Contractor shall only remove the quantities of roof that may be replaced within a shift.  Special weathertightness provisions need to be immediately implemented should weather activities prohibit further work.  Contractor shall be responsible for daily operations to include monitoring weather patterns and immediate weather protections and their maintenance during rain events.

- Permit requirements are the responsibility of the awarded contractor as listed on Section 800 Article 4.  WSU anticipates the Contractor will stay within the property and shouldn’t need City of Detroit Traffic or Engineering permitting.  Coordinate rerouting and signage for Emergency Vehicles/ Fire Lane access with WSU and City of Detroit Fire Department.

- Contractor must provide their own dumpster if needed, which must be rubber or plywood padded if placed on concrete.  Location and duration must be coordinated with the project manager.  Dumpster must be tagged with the name of your company clearly displayed. Any lawn damage must be restored.  Dumpster shall be privacy screened and contained within the site laydown area for crane.

- Questions are due by March 17, 2015  at 12:00 noon

- Bids are due no later than 2:00 p.m., March 24, 2015, at 5700 Cass Ave. Room 4200 AAB.  
No public bid opening will be held.

- Time of Completion: The Contract is expected to be fully executed on or about 15 calendar days after successful bidder qualification and recommendation of award.  The successful bidder (Contractor) agrees to start construction immediately after receipt of a fully executed contract and Purchase Order, and to complete the work as follows:  Substantial Completion, and State Approved Inspections (if appropriate), no later than June 30, 2015.

- A copy of the sign in sheet is available for downloading from the University Purchasing Web Site at  http://www.forms.purchasing.wayne.edu/Adv_bid/Adv_bid.html.

- This is an occupied area, awarded Contractor must be considerate of environment (noise, cleanliness, etc.).Some leaks in the existing roof led to the need to replace the roof at the Scott Hall, School of Medicine.

- Some storage may be coordinated with the project manager.   The intent is to have materials moved to the roof via crane.  The crane is to be on the East Side of the building.

- Replacement of the penthouse roof required.  Note, the elevator goes to the 9th floor.  Worker access  to the roof by stair and ladder.   The Access ladder and Roof hatch must be replaced as well.

- Note the crane is to be located in the fire lane area, NE corner of the building.  Fencing and signage required and re-routing of any pedestrian traffic.

- Due to the high traffic nature of this area, deliveries are to be coordinated around these high traffic periods.  Limited site storage is available across E. Canfield located in Parking Lot 75 near John R entrance.  Contractors must coordinate removal of existing items and new materials to keep any storage to a minimum.  Material Deliveries must be lifted to the roof, so as to minimize stored items at grade.  The loading dock must be maintained, i.e. daily usage it can’t be blocked.

- Work is to be done between the Memorial Day Holiday and the 4th of July, approximately 1 month.

- Note:  Areas to the east and south side of the building have underground parking and utilities as well as a tunnel to the Lande Building.  Care must be taken to avoid damage to them.  Care must be taken within limits of construction to ensure protection of existing conditions.  Contractor shall submit photo documentation of before and after construction conditions areas of activities and around staging and laydown areas.

- See drawings for the “no go zones”.  Roof sumps are being replaced as part of the base bid.  Additional supplemental roof drainage is by alternate.

- The Base Bid is to remove the mechanical unit.  Alternate 4 is a deduct to leave mechanical unit and flash in place.

IMPORTANT- This is an addendum which MUST be acknowledged on your bid form.

We will require two copies each of your lump sum proposals, vendor qualification questionnaire and your bid bond documents.

All questions concerning this project must be emailed to: Robert Kuhn, Sr. Buyer, Procurement & Strategic Sourcing.  Email: ac6243@wayne.edu, and copy Cynthia Branch, Buyer, at ab3577@wayne.edu.  Do not contact either FP&M or the Design Firm directly as this may result in disqualification of your proposal.

Thank you for interest shown in working with Wayne State University.

Robert Kuhn

Sr. Buyer

CC:	Robert Jacobs (Project Manager), Cynthia Branch, Buyer, Attendee list.